AQUARIUS CONDOMINIUM ASSOCIATION

Construction Committee Minutes February 1st, 2018.  Meeting Started at 11:10 am.

Attendees:

Construction Committee:  Zina Bluband, Sharon Smith, Alex Zoob, Pamela Ippolito, Leonard Finkelberg.

Members of the Board of Directors:  Buck Gupta, Linda Satz, Cecilio Berndsen, Judy Ort.

AP Management:  Adrian Paredes

Contractors:

- Hillman Engineering (Hillman): Scott Parmley, Jim Demiraj, Kevin DuBrey.

- Structural Preservation Systems, LLC (Structural): Andres Calvo

- Meeting was also attended by Unit Owners.

Hillman Engineering and Structural Preservation

1) Monthly construction schedule update (approval status).

2) Status on drawings for electrical plan as requested by permit reviewer.

3) Progress report on weekly construction activities (permanent items on agenda till project completed)

- Progress on rebuilding of balconies. Total up to date (#of corners and #of inside).

- Status on the alternative method of intrusion repairs. How many new intrusions?

- Status on pool deck construction, garage pours, deck pours.

- Status on pool construction.

4) Weekly information on any construction issues that may affect the owners.

- Any rain intrusions reported?

- Start date of construction on north tower.

- Drawings for tile's installation around balcony's railings post and the slope finish at the balcony's edge.

- Status on Hillman's release of the units with wall damage from electrical repairs.

Other items:

- Status on permit application for new Cooling towers.

- North tower service elevator modernization progress.

- South tower elevator modernization progress.

- Cleaning of the bare hallways floors.

- Any information on the beach service?

- North tower owners with Comcast cables running across the balconies should contact Comcast for cable rerouting to the inside of the units.

-----------------------------------------------------------------------------------------------------

1) Monthly update is expected in two weeks.  Hillman will provide comments and/or recommendations to the Structural on the scheduled timelines. Hopefully, in two weeks the Structural will be able to confirm the start of mobilization for north tower construction as in the middle of March.

2) Revised Electrical drawings for the pool deck have been submitted by Kevin DuBrey last Thursday.  Kevin met with the electrical plan reviewer who assured him that there should not be any more problems with the permit release. But permit was not released on Monday and Jean-Simon Berube of Structural is currently in the city of Hollywood building department addressing any outstanding issues.

3) Progress report on weekly construction activities.

- By Friday, February 2nd the concrete pour will be completed for 88 units.

- No new intrusions. Remains to be seen as pouring progresses.

- Correction of existing conditions of the deck (structure is not leveled) will delay pour on the deck by approximately two weeks.  Repairs are ongoing on beams, joists, and columns as well as partial replacement of garage slab on grade.

- Pool Construction status is dependent on construction of beams outside the pool and these that are next to the sea wall. Sea Wall continues undergoing repairs.

4) Weekly information on any construction issues that may affect the owners.

- No new intrusions due to the rain have been reported.

- The "pre-planning" meeting for the North Tower construction was held on January 23rd between the Hillman and the Structural. In two weeks the Structural will be able to confirm (or not) the start of mobilization for north tower construction as in the middle of March.

- Hillman provided package for the balcony's tile installation. This package includes the recommended architectural lay out, 3D rendering of the balcony and the engineering details with the instructions for the installation.  Adrian will distribute this package to the residents.  Residents will provide these details to the tile contractor of their choice. Main points: tile size does not have to be 12"X12".  Thickness of the tile cannot exceed 5/16". The installation of tile must start from the balcony's edge to ensure that full size tiles are running along this edge.  Hillman will make revisions to the drawing to incorporate allowance of the tile with 5/16 thickness. Adrian will forward for the owners one more estimate from the tile installer with price for labor only. Owners do not have to use this contractor. It is a courtesy call from the management trying to help owners who asked for the help.

- Work to repair walls damaged during the electrical rerouting is going to proceed as follows: Hillman starts inspection of the affected units today at 1:30pm.  The purpose of inspection is to verify scope of work as previously determined by the Structural.  Schedule of work has been distributed to the owners with understanding that more units will be added to this schedule as work progresses. Association began repairing damages due to the water intrusion during the Irma and the rains occurring after Irma. Baseboards will be replaced where needed, holes repaired, and drywall replaced where needed.  The cost of painting and finishes will be carried by the owners through the claim to their insurance company. Work commenced in the north tower. South tower residents will be notified on schedule when the time comes.

- Hillman's engineers recommended that due to the safety concerns the use of Plexiglas for the north tower should not be allowed.

Other items:  Update by the Property manager

- Contractor for cooling towers is in the city of Hollywood building department today addressing permit's issues with the reviewers.

- North Tower Service elevator: Track and ropes are installed. Originally ordered cab shell was damaged during the transportation. New cab shell is scheduled for delivery next week. Elevator pit repairs related to the water accumulation have been scheduled.  Current anticipated completion date is February 22nd.

- South tower elevator modernization progresses as planned. Passenger cab was ordered.

- Cleaning of the hallways floor is in progress. It is slow process as the cleaning crew is moving through each floor.

- Nothing new on the issue of the beach service.

- Unit owners in the north tower with Comcast cables running across balcony have experienced major difficulties with the Comcast service.  It seems almost impossible to get in contact with the Comcast to have cables rerouted to the inside of unit.  Property manager will attempt to obtain a direct line access to the Comcast. If successful, this number will be shared with the owners. Meanwhile the residents in North tower with cables running across the balconies should register in the office.

Meeting adjourned at 12:35pm.

Signed: Zina Bluband